## Project Tasks
Task | Owner | Deadline | Status
Requirements Gathering | Emily Torres | 2025-01-15 | Completed
System Architecture Design | James Whitfield | 2025-01-30 | Completed
Database Schema Draft | Priya Nair | 2025-02-10 | Completed
API Endpoint Specification | Marco Delgado | 2025-02-20 | Completed
Frontend Prototype | Sarah Chen | 2025-03-05 | Completed
Backend Core Module | Liam O'Brien | 2025-03-25 | In Progress
Unit Test Suite | Ayesha Rahman | 2025-04-10 | In Progress
Integration Testing | Derek Nguyen | 2025-04-25 | Not Started
Security Audit | Fatima Al-Hassan | 2025-05-05 | Not Started
Performance Benchmarking | Marcus Johnson | 2025-05-15 | Not Started
User Acceptance Testing | Clara Petrov | 2025-05-30 | Not Started
Deployment Pipeline Setup | Hiroshi Tanaka | 2025-06-10 | Not Started
Documentation Review | Amara Osei | 2025-06-20 | Not Started
Stakeholder Demo Preparation | Emily Torres | 2025-06-28 | Not Started
Go-Live Release | James Whitfield | 2025-07-01 | Not Started